## Start Here
ECP Event Planning Critical Path
A practical control document for managing event tasks, deadlines, ownership and dependencies.
How to Use This Workbook
1 | Use the Critical Path sheet as the central planning control document. Add, delete or adapt tasks to fit your event.
2 | Assign an owner and due date to each task. Use Dependency to identify work that must happen first.
3 | Update Status throughout planning. Filter by Workstream, Owner or Status when you need a focused view.
4 | Use ECP Resource / Tool to identify the working document that contains the operational detail. The Critical Path should not duplicate those tools.
5 | Use Key Milestones for the few dates that the entire team needs to see quickly.
Status Definitions
Not Started | Work has not begun.
In Progress | Work is actively underway.
Waiting | Work is paused pending information, approval or another task.
Complete | The task is finished.
Not Applicable | The task does not apply to this event.
ECP planning principle: the Critical Path tracks the work; supporting templates contain the detail. AI can assist with research, drafting, comparison and analysis, but event fundamentals and professional judgment remain essential.
Dates: Enter dates directly in the Due Date or Target Date cells (for example, 9/24/2026). Excel will display them consistently as Sep 24, 2026.

## Event Information
ECP Event Information for AI
Complete this short event profile, then upload it with the ECP Event Planning Critical Path to help AI create a starting Critical Path.
Event Information | Your Event | Guidance
Event Name |  | Name of the event
Event Type |  | Select the closest option
Event Date |  | Enter the confirmed or anticipated event date
Location / City |  | Enter the city/location or TBD
Event Format |  | Select the event format
Expected Attendance |  | Enter the estimated number of attendees
Event Purpose |  | In 1–2 sentences, explain why the event is being held
Event Description |  | Briefly describe what will happen at the event
Planning Stage |  | Select the stage that best describes the event
Known Event Elements |  | Select one below, then add other known elements in Other Important Information
Already Confirmed |  | Briefly list anything already confirmed, or enter None
Other Important Information |  | Add anything else AI should consider when suggesting the Critical Path
Copy-and-Paste ECP Prompt
Using the event information provided and the attached ECP Event Planning Critical Path Template, help me create a starting Critical Path for this event. Review the existing ECP tasks and identify which appear relevant to this event. Suggest reasonable target dates by working backward from the event date and identify dependencies where appropriate. Do not invent information that has not been provided. Leave unknown information for me to complete or flag it for my review. Do not assign individual names as task owners unless they have been provided. I will review and customize the Critical Path before using it.
Complete → Upload with Critical Path → Copy Prompt → Review AI Suggestions

## Critical Path
ECP Event Planning Critical Path
Workstream | Task | Due Date | Owner | Status | Dependency | ECP Resource / Tool | Notes
Event Foundation | Define event purpose and objectives |  |  | Not Started |  | Event Brief / Foundation Template
Event Foundation | Identify target audience and key stakeholders |  |  | Not Started |  | Event Brief / Foundation Template
Event Foundation | Confirm decision-makers |  |  | Not Started |  | Event Brief / Foundation Template
Event Foundation | Determine event format |  |  | Not Started |  | Event Brief / Foundation Template
Event Foundation | Establish preferred date(s) and duration |  |  | Not Started |  | Event Brief / Foundation Template
Event Foundation | Establish estimated attendance |  |  | Not Started |  | Event Brief / Foundation Template
Event Foundation | Identify location requirements |  |  | Not Started |  | Event Brief / Foundation Template
Event Foundation | Identify accessibility and language requirements |  |  | Not Started |  | Event Brief / Foundation Template
Event Foundation | Establish preliminary budget |  |  | Not Started |  | Event Budget Template
Event Foundation | Identify major requirements and constraints |  |  | Not Started |  | Event Brief / Foundation Template
Event Foundation | Confirm planning team and roles |  |  | Not Started |  | Event Brief / Foundation Template
Event Foundation | Establish planning timeline |  |  | Not Started |  | Critical Path
Program | Develop preliminary program framework |  |  | Not Started |  | Preliminary Program Framework Template
Program | Identify program components and session objectives |  |  | Not Started |  | Preliminary Program Framework Template
Program | Determine session formats |  |  | Not Started |  | Preliminary Program Framework Template
Program | Develop draft agenda |  |  | Not Started |  | Agenda Template
Program | Confirm program timing and transitions |  |  | Not Started |  | Agenda Template
Program | Identify speakers, moderators and facilitators |  |  | Not Started |  | Speaker Research & Selection Template
Program | Coordinate program requirements with other workstreams |  |  | Not Started |  | Preliminary Program Framework Template
Program | Establish program approval process |  |  | Not Started
Program | Confirm final program |  |  | Not Started |  | Agenda Template
Program | Maintain program changes |  |  | Not Started |  | Agenda Template
Program | Develop detailed Run of Show when required |  |  | Not Started |  | Run of Show (future ECP resource)
Venue | Confirm venue requirements |  |  | Not Started |  | Venue Requirements Checklist
Venue | Research potential venues |  |  | Not Started |  | Venue Requirements Checklist
Venue | Prepare and issue venue RFP |  |  | Not Started |  | Venue RFP Template
Venue | Manage RFP questions and responses |  |  | Not Started |  | Venue RFP Template
Venue | Review proposals |  |  | Not Started |  | Proposal & Cost Comparison Template
Venue | Compare proposals and costs |  |  | Not Started |  | Proposal & Cost Comparison Template
Venue | Conduct site visits if required |  |  | Not Started |  | Venue Site Visit Checklist
Venue | Identify preferred venue |  |  | Not Started |  | Proposal & Cost Comparison Template
Venue | Negotiate and review contract |  |  | Not Started |  | Venue Contract Review Checklist
Venue | Obtain approval and confirm venue |  |  | Not Started
Venue | Track contractual deadlines |  |  | Not Started |  | Critical Path
Venue | Update venue requirements as planning progresses |  |  | Not Started |  | Venue Requirements Checklist
Venue | Finalize function sheets |  |  | Not Started |  | Function Sheet Template
Logistics | Identify logistics requirements |  |  | Not Started |  | Logistics Planning Checklist
Logistics | Determine room and setup requirements |  |  | Not Started |  | Room Setup Guide / Checklist
Logistics | Determine registration and check-in requirements |  |  | Not Started |  | Logistics Planning Checklist
Logistics | Determine signage requirements |  |  | Not Started |  | Signage Planning Matrix
Logistics | Plan attendee movement and flow |  |  | Not Started |  | Logistics Planning Checklist
Logistics | Identify accessibility logistics |  |  | Not Started |  | Logistics Planning Checklist
Logistics | Determine transportation requirements if applicable |  |  | Not Started |  | Logistics Planning Checklist
Logistics | Determine shipping, receiving and storage requirements |  |  | Not Started |  | Logistics Planning Checklist
Logistics | Coordinate event materials and supplies |  |  | Not Started |  | Logistics Planning Checklist
Logistics | Determine staffing and volunteer requirements |  |  | Not Started |  | Event Staffing Plan
Logistics | Establish setup and teardown requirements |  |  | Not Started |  | Setup & Teardown Checklist
AV | Establish AV requirements |  |  | Not Started |  | AV Requirements Checklist
AV | Determine AV needs by room and session |  |  | Not Started |  | AV Requirements Matrix
AV | Confirm in-house AV arrangements and restrictions |  |  | Not Started |  | AV Requirements Checklist
AV | Determine whether outside AV supplier is required |  |  | Not Started |  | AV Requirements Checklist
AV | Prepare and issue AV RFP when required |  |  | Not Started |  | AV RFP Template
AV | Review and compare proposals and costs |  |  | Not Started |  | Proposal & Cost Comparison Template
AV | Select and contract AV supplier |  |  | Not Started
AV | Finalize AV requirements |  |  | Not Started |  | AV Requirements Matrix
AV | Establish presentation management process |  |  | Not Started |  | Presentation Management Checklist
AV | Confirm presenter technical requirements |  |  | Not Started |  | AV Requirements Matrix
AV | Establish testing and rehearsal requirements |  |  | Not Started |  | AV Requirements Matrix
AV | Review final AV order and costs |  |  | Not Started |  | AV Requirements Matrix
Event Technology | Identify event technology requirements |  |  | Not Started |  | Event Technology Requirements Checklist
Event Technology | Determine registration technology needs |  |  | Not Started |  | Event Technology Requirements Checklist
Event Technology | Determine event app requirements |  |  | Not Started |  | Event Technology Requirements Checklist
Event Technology | Determine virtual or hybrid technology needs if applicable |  |  | Not Started |  | Event Technology Requirements Checklist
Event Technology | Determine attendee engagement technology needs |  |  | Not Started |  | Event Technology Requirements Checklist
Event Technology | Determine survey and evaluation technology needs |  |  | Not Started |  | Event Technology Requirements Checklist
Event Technology | Research and select required technology |  |  | Not Started |  | Event Technology Requirements Checklist
Event Technology | Identify integration requirements |  |  | Not Started |  | Event Technology Requirements Checklist
Event Technology | Establish data and privacy requirements |  |  | Not Started |  | Event Technology & Data Checklist
Event Technology | Configure required systems |  |  | Not Started
Event Technology | Develop attendee-facing technology content |  |  | Not Started
Event Technology | Test systems, links, forms and integrations |  |  | Not Started
Event Technology | Establish support and contingency processes |  |  | Not Started
Event Technology | Complete final technology testing |  |  | Not Started |  | Event Readiness Checklist
Food & Beverage | Establish F&B requirements |  |  | Not Started |  | F&B Planning Checklist
Food & Beverage | Establish preliminary F&B budget |  |  | Not Started |  | Event Budget Template
Food & Beverage | Review menu and service options |  |  | Not Started |  | F&B Planning Checklist
Food & Beverage | Determine service style |  |  | Not Started |  | F&B Planning Checklist
Food & Beverage | Develop preliminary menu |  |  | Not Started |  | F&B Planning Checklist
Food & Beverage | Establish dietary and allergy process |  |  | Not Started |  | Dietary Requirements Checklist
Food & Beverage | Determine beverage requirements |  |  | Not Started |  | F&B Planning Checklist
Food & Beverage | Coordinate F&B timing with program |  |  | Not Started |  | F&B Planning Checklist
Food & Beverage | Review estimated costs |  |  | Not Started |  | Event Budget Template
Food & Beverage | Confirm menu |  |  | Not Started |  | F&B Planning Checklist
Food & Beverage | Track guarantee deadline |  |  | Not Started |  | Critical Path
Food & Beverage | Submit final guarantees and dietary requirements |  |  | Not Started |  | Dietary Requirements Checklist
Food & Beverage | Review and approve final BEO |  |  | Not Started |  | BEO Review Checklist
Speakers | Establish speaker requirements |  |  | Not Started |  | Speaker Research & Selection Template
Speakers | Research potential speakers and sources |  |  | Not Started |  | Speaker Research & Selection Template
Speakers | Develop shortlist |  |  | Not Started |  | Speaker Research & Selection Template
Speakers | Invite and contact speakers |  |  | Not Started |  | Speaker Invitation Template
Speakers | Confirm participation |  |  | Not Started |  | Speaker Management Tracker
Speakers | Confirm terms and requirements |  |  | Not Started |  | Speaker Agreement Checklist
Speakers | Complete agreements where required |  |  | Not Started |  | Speaker Agreement Checklist
Speakers | Confirm honorarium and fees |  |  | Not Started |  | Speaker Management Tracker
Speakers | Confirm travel and accommodation requirements |  |  | Not Started |  | Speaker Management Tracker
Speakers | Collect required speaker information and materials |  |  | Not Started |  | Speaker Management Tracker
Speakers | Track speaker deliverables |  |  | Not Started |  | Speaker Management Tracker
Speakers | Provide speaker briefing |  |  | Not Started |  | Speaker Briefing Template
Speakers | Confirm technical requirements |  |  | Not Started |  | Speaker Management Tracker
Speakers | Confirm permissions |  |  | Not Started |  | Speaker Management Tracker
Speakers | Complete final speaker confirmation |  |  | Not Started |  | Speaker Management Tracker
Communications | Identify communication audiences |  |  | Not Started |  | Event Communications Planner
Communications | Determine required communications |  |  | Not Started |  | Event Communications Planner
Communications | Establish communications timeline |  |  | Not Started |  | Event Communications Timeline
Communications | Confirm key messages |  |  | Not Started |  | Event Communications Planner
Communications | Prepare launch and invitation communications |  |  | Not Started
Communications | Prepare registration and confirmation communications |  |  | Not Started
Communications | Schedule attendee updates and reminders |  |  | Not Started |  | Event Communications Timeline
Communications | Coordinate stakeholder and VIP communications where required |  |  | Not Started |  | Event Communications Planner
Communications | Prepare pre-event and final attendee information |  |  | Not Started |  | Pre-Event Communication Checklist
Communications | Prepare onsite communications |  |  | Not Started |  | Event Communications Planner
Communications | Establish last-minute and emergency communication process |  |  | Not Started |  | Event Communications Planner
Communications | Prepare post-event communications |  |  | Not Started |  | Event Communications Planner
Budget | Establish preliminary event budget |  |  | Not Started |  | Event Budget Template
Budget | Develop initial estimates |  |  | Not Started |  | Event Budget Template
Budget | Establish contingency |  |  | Not Started |  | Event Budget Template
Budget | Track supplier estimates and proposals |  |  | Not Started |  | Proposal & Cost Comparison Template
Budget | Compare supplier proposals and costs |  |  | Not Started |  | Proposal & Cost Comparison Template
Budget | Update budget following supplier selections |  |  | Not Started |  | Event Budget Template
Budget | Record contractual commitments |  |  | Not Started |  | Event Budget Template
Budget | Record deposit requirements |  |  | Not Started |  | Event Budget Template
Budget | Track and confirm deposits |  |  | Not Started |  | Event Budget Template
Budget | Track staged or interim payments |  |  | Not Started |  | Event Budget Template
Budget | Track final-payment deadlines |  |  | Not Started |  | Event Budget Template
Budget | Monitor estimated, committed and actual costs |  |  | Not Started |  | Event Budget Template
Budget | Monitor variances |  |  | Not Started |  | Event Budget Template
Budget | Update forecast |  |  | Not Started |  | Event Budget Template
Budget | Reconcile final invoices against approved or contracted costs |  |  | Not Started |  | Event Budget Template
Budget | Confirm final payments |  |  | Not Started |  | Event Budget Template
Budget | Close and reconcile event budget |  |  | Not Started |  | Event Budget Template
Event Delivery & Readiness | Complete final event readiness review |  |  | Not Started |  | Event Readiness Checklist
Event Delivery & Readiness | Finalize Function Sheets |  |  | Not Started |  | Function Sheet Template
Event Delivery & Readiness | Finalize Run of Show and script |  |  | Not Started |  | Run of Show (future ECP resource)
Event Delivery & Readiness | Confirm final details with vendors and suppliers |  |  | Not Started |  | Vendor Final Confirmation Checklist
Event Delivery & Readiness | Confirm speakers and key participants |  |  | Not Started |  | Speaker Management Tracker
Event Delivery & Readiness | Confirm staffing and onsite responsibilities |  |  | Not Started |  | Event Staffing Plan
Event Delivery & Readiness | Confirm contingency and emergency plan |  |  | Not Started |  | Event Contingency Plan
Event Delivery & Readiness | Conduct final team briefing |  |  | Not Started |  | Event Team Briefing Template
Event Delivery & Readiness | Complete required rehearsals and technical testing |  |  | Not Started |  | Run of Show / AV Requirements (future ECP resource where applicable)
Event Delivery & Readiness | Manage setup |  |  | Not Started
Event Delivery & Readiness | Deliver and manage event |  |  | Not Started
Event Delivery & Readiness | Manage event close and teardown |  |  | Not Started
Event Delivery & Readiness | Record outstanding follow-up items |  |  | Not Started
Post-Event & Evaluation | Complete outstanding event follow-up |  |  | Not Started
Post-Event & Evaluation | Send post-event communications |  |  | Not Started |  | Event Communications Planner
Post-Event & Evaluation | Develop and distribute evaluation or survey where appropriate |  |  | Not Started |  | Post-Event Evaluation & Lessons Learned Template
Post-Event & Evaluation | Collect event results and feedback |  |  | Not Started |  | Post-Event Evaluation & Lessons Learned Template
Post-Event & Evaluation | Analyze results against event objectives |  |  | Not Started |  | Post-Event Evaluation & Lessons Learned Template
Post-Event & Evaluation | Complete supplier and vendor follow-up |  |  | Not Started
Post-Event & Evaluation | Reconcile final invoices and payments |  |  | Not Started |  | Event Budget Template
Post-Event & Evaluation | Conduct team debrief |  |  | Not Started |  | Post-Event Evaluation & Lessons Learned Template
Post-Event & Evaluation | Document lessons learned |  |  | Not Started |  | Post-Event Evaluation & Lessons Learned Template
Post-Event & Evaluation | Develop recommendations for future events |  |  | Not Started |  | Post-Event Evaluation & Lessons Learned Template
Post-Event & Evaluation | Archive relevant event records and resources |  |  | Not Started
Post-Event & Evaluation | Close event |  |  | Not Started

## Key Milestones
ECP Key Milestones
Use this sheet for the few dates that need to remain visible across the entire planning team.
Milestone | Target Date | Owner | Status | Related Workstream | Notes
Event objectives approved |  |  | Not Started | Event Foundation
Program framework approved |  |  | Not Started | Program
Venue contracted |  |  | Not Started | Venue
Major suppliers contracted |  |  | Not Started | Logistics
Registration / attendee technology ready |  |  | Not Started | Event Technology
Final program confirmed |  |  | Not Started | Program
Final guarantees due |  |  | Not Started | Food & Beverage
Final vendor payments / deposits due |  |  | Not Started | Budget
Run of Show finalized |  |  | Not Started | Event Delivery & Readiness
Final readiness review |  |  | Not Started | Event Delivery & Readiness
Event day |  |  | Not Started | Event Delivery & Readiness
Post-event evaluation complete |  |  | Not Started | Post-Event & Evaluation

## AI Can Assist
AI Can Assist — Critical Path
Optional: use AI to help create a starting point for your Critical Path. This workbook can be used without AI. The planner reviews, verifies and decides what belongs in the final Critical Path.
Step | What to Do | Planner Guidance
1 | Complete Event Information | Enter the facts you know about the event. Leave unknown information blank or to be confirmed.
2 | Upload the workbook | Upload the complete ECP workbook to an AI tool that can read spreadsheet files.
3 | Copy the ECP prompt | Use the prompt below with the workbook to ask AI for a starting Critical Path.
4 | Review the suggestions | Check suggested tasks, dates, dependencies and assumptions against your event requirements.
5 | Apply professional judgment | Customize the Critical Path before using it as your event planning control document.
Copy-and-Paste ECP Prompt
Using the information provided in the Event Information worksheet of this workbook, help me create a starting Critical Path for this event. Review the existing ECP tasks in the Critical Path worksheet and identify which tasks appear relevant to this event. Keep the existing ECP workstreams and task structure. Suggest reasonable target dates by working backward from the event date and identify dependencies where appropriate. Do not invent information that has not been provided. Leave unknown information for me to complete or flag it for my review. Do not assign individual names as task owners unless they have been provided. Do not modify the workbook automatically. Present suggestions for planner review.
AI CAN ASSIST | PLANNER VERIFIES | PLANNER DECIDES
Organize known information, identify relevant existing tasks, suggest starting dates and dependencies, and flag gaps for review. | Check relevance, sequence, deadlines, dependencies, ownership and anything AI has assumed or missed. | Add, remove or adapt tasks, confirm dates and owners, and maintain the Critical Path as the working control document.
ECP principle: Know the work. Use AI to support the work. Know enough to judge the result.

## Lists
Workstreams | Statuses | Helper lists — do not edit unless changing dropdown options.
Event Foundation | Not Started
Program | In Progress
Venue | Waiting
Logistics | Complete
AV | Not Applicable
Event Technology
Food & Beverage
Speakers
Communications
Budget
Event Delivery & Readiness
Post-Event & Evaluation