## Start Here
ECP Event Readiness Checklist
Purpose
Use this checklist shortly before event delivery to confirm that the key items required to deliver the event are complete and to identify anything that still requires action.
How to Use
1 | Review the Event Planning Critical Path and bring forward the key items that must be complete before event delivery.
2 | Use the pre-populated ECP readiness items as a final check. Add, remove or adapt items for the event.
3 | Mark Completed when the item has been confirmed.
4 | Select Yes under Action Required? when something remains outstanding.
5 | Use Notes to state what still needs to be done, clarified or confirmed.
AI Can Assist
Optional AI guidance and the ECP copy-and-paste prompt are available on the AI Can Assist worksheet.
ECP workflow: Critical Path → key delivery items → Event Readiness Checklist → resolve outstanding actions → Event Delivery

## Event Readiness
ECP Event Readiness Checklist
Readiness Item | Owner | Deadline | Completed ✓ | Action Required? | Notes
Venue & Logistics
Venue contract and key contractual requirements confirmed |  |  | FALSE
Final room assignments and setup requirements confirmed |  |  | FALSE
Registration / check-in arrangements confirmed |  |  | FALSE
Signage, event materials and supplies ready |  |  | FALSE
Shipping, receiving, storage and access arrangements confirmed |  |  | FALSE
Setup and teardown timing confirmed |  |  | FALSE
Program & Speakers
Final program / agenda confirmed |  |  | FALSE
Run of Show finalized where required |  |  | FALSE
Speakers, moderators and key participants reconfirmed |  |  | FALSE
Required speaker materials / presentations received |  |  | FALSE
Speaker travel, honorarium and other agreed requirements addressed |  |  | FALSE
Final speaker briefing completed |  |  | FALSE
AV & Event Technology
Final AV order reviewed and confirmed |  |  | FALSE
Presentation management process confirmed |  |  | FALSE
Presentations / media files sent to AV |  |  | FALSE
Required event technology configured and tested |  |  | FALSE
Technical testing / rehearsal completed where required |  |  | FALSE
Technology / AV contingency arrangements confirmed |  |  | FALSE
Food & Beverage
Final menu and service requirements confirmed |  |  | FALSE
Final guarantees submitted |  |  | FALSE
Dietary and allergy requirements confirmed |  |  | FALSE
Final BEO / catering order reviewed and approved |  |  | FALSE
Attendee Experience & Communications
Final attendee information / communications sent |  |  | FALSE
Accessibility and language requirements addressed |  |  | FALSE
Registration / attendee lists ready |  |  | FALSE
Directional and onsite attendee information ready |  |  | FALSE
Last-minute / emergency communication process confirmed |  |  | FALSE
Team & Suppliers |  |  | FALSE
All key suppliers / vendors reconfirmed |  |  | FALSE
Supplier onsite contacts available |  |  | FALSE
Staff / volunteer assignments confirmed |  |  | FALSE
Final team briefing completed |  |  | FALSE
Onsite roles and responsibilities confirmed |  |  | FALSE
Event Delivery & Contingency |  |  | FALSE
Final Function Sheet(s) completed |  |  | FALSE
Event Readiness review completed |  |  | FALSE
Contingency / emergency plan confirmed |  |  | FALSE
Key contact list available to onsite team |  |  | FALSE
Setup plan confirmed |  |  | FALSE
Outstanding follow-up items identified and assigned |  |  | FALSE
Financial & Contractual |  |  | FALSE
Required deposits and staged payments completed |  |  | FALSE
Outstanding payment deadlines confirmed |  |  | FALSE
Final supplier orders and estimated costs reviewed |  |  | FALSE
Outstanding contractual requirements / deadlines addressed |  |  | FALSE

## AI Can Assist
AI Can Assist — Event Readiness
Optional: use AI to help identify possible readiness items and gaps. This toolkit works completely on its own. AI does not confirm completion or decide whether the event is ready.
Step | What to Do | Planner Guidance
1 | Prepare the source documents | Use the latest Critical Path, Final Program & Agenda and other final planning documents relevant to the event.
2 | Upload the documents | If you choose to use AI, upload the relevant documents together with this ECP Event Readiness Checklist.
3 | Copy the ECP prompt | Use the prompt below to ask AI to review the source information and suggest possible readiness items, gaps or unresolved information.
4 | Planner verifies | Check every suggestion against the actual event status and confirm with the event team, venue or suppliers where necessary.
5 | Planner decides | Update Completed, Action Required? and Notes. Resolve or manage outstanding items before finalizing delivery documents.
Copy-and-Paste ECP Prompt
Using the ECP Event Readiness Checklist together with the Critical Path, Final Program & Agenda and other final planning documents I provide, help me identify possible readiness items, gaps or unresolved information that should be reviewed before event delivery. Review the existing readiness items first. Identify which items appear relevant to this event and suggest any additional readiness items that may be missing based only on the information in the documents. For each possible gap or unresolved item, identify the source information that led you to flag it and what requires planner review, confirmation or follow-up. Do not assume that an item is complete simply because it appears in a planning document. Do not mark anything complete and do not decide whether the event is ready.
AI CAN ASSIST | PLANNER VERIFIES | PLANNER DECIDES
Review final planning documents, organize possible readiness items, and flag gaps or unresolved information. | Confirm each item against the actual event status and with the appropriate team, venue or supplier. | Determine what is complete, what requires action and what must be resolved or managed before event delivery.
ECP principle: Know the work. Use AI to support the work. Know enough to judge the result.